## Sheet1
Track | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Applications and Data | Planning | Discovery Workshops | Discovery Workshops | Design | Design | Design/Documentation | Documentation | Documentation/Review
ITSM | Planning | Discovery Workshops | Discovery Workshops | Design | Design | Design/Documentation | Documentation | Documentation/Review
Cloud Governance | Planning | Discovery Workshops | Discovery Workshops | Design | Design | Design/Documentation | Documentation | Documentation/Review
Cloud Foundarions and Architeture | Planning | Discovery Workshops | Discovery Workshops | Design | Design | Design/Documentation | Documentation | Documentation/Review
M365 | Planning | Discovery Workshops | Discovery Workshops | Design | Design | Design/Documentation | Documentation | Documentation/Review
DWP | Planning | Discovery Workshops | Discovery Workshops | Design | Design | Design/Documentation | Documentation | Documentation/Review
Security/Identity | Planning | Discovery Workshops | Discovery Workshops | Design | Design | Design/Documentation | Documentation | Documentation/Review

## Sheet2
Track | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
Oversight & Program Management
Governance
Cloud Governance Planning
Cloud Implementation Strategy
Cloud FinOps Model
Cloud Governance Design
RBAC Model
Change Process for Azure
Documentation
Review
Identity
Identity Foundations
Review Current Identity Needs
Review Current AD needs
Review Application Identity Needs
Identity Design
Azure IDM Planning/Design
Self Service Planning
Azure Entra Design (domain)
Azure Conditional Access Design
Azure MFA Design
User Ingestion from Workday Design
Documentation
Review
Security
Security Foundations
Cloud Defender For Azure Planning
Azure Sentinel Planning
IDM Strategy Planning
Defender for Endpoint Planning
Cloud App Security Deployment Planning
Security Design
Azure Sentinel Connections Design
Alerts and Hunting Design
Rules and Policy Design
Documentation
Review
Cloud Foundations
Cloud Planning
CAF
WAF
Governance
Inventory
Cloud Design
Backup and DR Design
Azure Management Design
Application Migration Design
Server (IaaS) Migration Design
SQL (PaaS) Migration Design
Develop Migration Plan
Azure Virtual Desktop Architecture
Network Architecture
Documentation
Review
M365
M365 Planning
M365 Source Tenant Configuration Review
M365 Target Tenant Configuration Review
M365 Source Security & Compliance Configuration Review
M365 Target Security & Compliance Configuration Review
Exchange Online Assessment
SharePoint Online Assessment
OneDrive Assessment
Teams Assessment
M365 Design
Internal Migration Tooling KT and Design
Design M365 Security & Compliance Configuration
Design Exchange Online Migration Process and Plan
Design SharePoint Online Online Migration Process and Plan
Design OneDrive Migration Process and Plan
Design Teams Channels Migration Process and Plan
Design Teams Chat Migration Process and Plan
Develop Migration Process and Plan Design Documentation
Documentation
Review
DWP
Intune Foundations Planning
EM+S Validation and Planning
Devices and Policies Planning
AutoPilot Planning
Intune Foundations Design
Devce Enrollment Design
Device Rules and Polies Design
Device Migration Design
AutoPilot Design
Documentation
Review
Applications
Application Planning
Application Rationlization
DevOps Planning
Application Design
Application Migration Design
Application Architecture Design
Application Database Design
Documentation
Review
ITSM
ITSM Planning
ITSM Design
Documentation
Review